## Ark1
Weekday | tir | ons | tor | fre | lør | søn | man | tir | ons | tor | fre | lør | søn | man | tir | ons | tor | fre | lør | søn | man | tir | ons | tor | fre
Date | 2014-02-25 | 2014-02-26 | 2014-02-27 | 2014-02-28 | 2014-03-01 | 2014-03-02 | 2014-03-03 | 2014-03-04 | 2014-03-05 | 2014-03-06 | 2014-03-07 | 2014-03-08 | 2014-03-09 | 2014-03-10 | 2014-03-11 | 2014-03-12 | 2014-03-13 | 2014-03-14 | 2014-03-15 | 2014-03-16 | 2014-03-17 | 2014-03-18 | 2014-03-19 | 2014-03-20 | 2014-03-21
Workhours | 2014-02-25: 10; 2014-02-26: 30; 2014-02-27: 30; 2014-02-28: 32; 2014-03-01: 0; 2014-03-02: 2; 2014-03-03: 30; 2014-03-04: 29; 2014-03-05: 27; 2014-03-06: 0; 2014-03-07: 0; 2014-03-08: 0; 2014-03-09: 0; 2014-03-10: 0
What
Documentation | 2014-03-04: 2; 2014-03-05: 1
Roombooking and administration | 2014-02-25: 10
PU1 | 2014-02-26: 30; 2014-02-27: 6; 2014-03-02: 1; 2014-03-05: 4
PU2 | 2014-02-27: 24; 2014-02-28: 15; 2014-03-02: 1; 2014-03-05: 1
KTN classdiagram | 2014-02-28: 10
KTN sekvensdiagram | 2014-02-28: 5
KTN a short textual design | 2014-02-28: 2
KTN part 1 completion | 2014-03-03: 4
Discuss how we want the user interface | 2014-03-03: 4
Designing the user interface using paper models | 2014-03-03: 10; 2014-03-04: 10; 2014-03-05: 6
Create ER-diagram for the application and requirements. | 2014-03-03: 8; 2014-03-04: 4
PU3 (superiordesign) | 2014-03-03: 4
DB2: Mysql | 2014-03-04: 8; 2014-03-05: 1
Show papermodel to studass | 2014-03-04: 5
PU 1-3 evaluation | 2014-03-05: 5
Papermodel evaluation with other group | 2014-03-05: 5
KTN Implementation user and server | 2014-03-05: 2
Implementation of helper classes for all sections. | 2014-03-05: 2
357 beregnet av deloppgavene…
KTN classdiagram. We were pretty unusre of the task and therfore used more time.
4.03 --> One person sick another one occupied in meetings.