## Ark1
Weekday | Total | tir | ons | tor | fre | lør | søn | man | tir | ons | tor | fre | lør | søn | man | tir | ons | tor | fre | lør | søn | man | tir | ons | tor | fre
Date |  | 2014-02-25 | 2014-02-26 | 2014-02-27 | 2014-02-28 | 2014-03-01 | 2014-03-02 | 2014-03-03 | 2014-03-04 | 2014-03-05 | 2014-03-06 | 2014-03-07 | 2014-03-08 | 2014-03-09 | 2014-03-10 | 2014-03-11 | 2014-03-12 | 2014-03-13 | 2014-03-14 | 2014-03-15 | 2014-03-16 | 2014-03-17 | 2014-03-18 | 2014-03-19 | 2014-03-20 | 2014-03-21
Workhours | 567 | 10 | 30 | 30 | 32 | 0 | 2 | 30 | 29 | 27 | 37 | 0 | 0 | 0 | 36 | 40 | 30 | 28 | 24 | 0 | 0 | 30 | 32 | 38 | 39 | 43
What | 0 | 2014-03-13: Få folk
Documentation | 9 | 2014-03-04: 2; 2014-03-05: 1; 2014-03-06: 1; 2014-03-10: 1; 2014-03-11: 1; 2014-03-12: 1; 2014-03-17: 1; 2014-03-21: 1
Roombooking and administration | 10 | 2014-02-25: 10
PU1 | 41 | 2014-02-26: 30; 2014-02-27: 6; 2014-03-02: 1; 2014-03-05: 4
PU2 | 41 | 2014-02-27: 24; 2014-02-28: 15; 2014-03-02: 1; 2014-03-05: 1
KTN classdiagram | 10 | 2014-02-28: 10
KTN sekvensdiagram | 5 | 2014-02-28: 5
KTN a short textual design | 2 | 2014-02-28: 2
KTN part 1 completion | 4 | 2014-03-03: 4
Discuss how we want the user interface | 4 | 2014-03-03: 4
Designing the user interface using paper models | 26 | 2014-03-03: 10; 2014-03-04: 10; 2014-03-05: 6
Create ER-diagram for the application and requirements. | 12 | 2014-03-03: 8; 2014-03-04: 4
PU3 (superiordesign) | 4 | 2014-03-03: 4
DB2: Mysql | 9 | 2014-03-04: 8; 2014-03-05: 1
Show papermodel to studass | 5 | 2014-03-04: 5
PU 1-3 evaluation | 5 | 2014-03-05: 5
Papermodel evaluation with other group | 5 | 2014-03-05: 5
KTN Implementation user and server login | 13 | 2014-03-05: 2; 2014-03-06: 4; 2014-03-10: 7
Implementation of helper classes for all sections. | 2 | 2014-03-05: 2
MMI Report | 14 | 2014-03-06: 14
Java fx installation and understanding… | 11 | 2014-03-06: 11
Java fx screen design | 81 | 2014-03-10: 14; 2014-03-11: 25; 2014-03-12: 18; 2014-03-13: 12; 2014-03-14: 12
DB: Implementation of database in java. | 60 | 2014-03-06: 7; 2014-03-10: 7; 2014-03-11: 10; 2014-03-12: 6; 2014-03-13: 6; 2014-03-14: 6; 2014-03-17: 6; 2014-03-18: 6; 2014-03-19: 6
New requirment mail | 7 | 2014-03-10: 7
KTN: JSON in java | 10 | 2014-03-11: 4; 2014-03-12: 2; 2014-03-13: 4
KTN: Server and client | 15 | 2014-03-12: 3; 2014-03-13: 6; 2014-03-14: 6
KTN: Functionality for GUI class | 17 | 2014-03-17: 6; 2014-03-18: 6; 2014-03-19: 2; 2014-03-20: 2; 2014-03-21: 1
Java fx: Main screen | 30 | 2014-03-17: 6; 2014-03-18: 6; 2014-03-19: 14; 2014-03-20: 4
Java fx: Viewscreen and logic | 18 | 2014-03-17: 6; 2014-03-18: 6; 2014-03-19: 6
Java fx: Editscreen | 18 | 2014-03-18: 6; 2014-03-19: 6; 2014-03-20: 6
Mail class: | 6 | 2014-03-17: 6
Integration database and network | 6 | 2014-03-18: 2; 2014-03-19: 4
Integration and testing GUI and backend: Calendar screen | 18 | 2014-03-20: 18
Integration and testing GUI and backend: View appointment | 8 | 2014-03-21: 8
Integration and testing GUI and backend: Edit appointment | 8 | 2014-03-21: 8
PU 5: | 11 | 2014-03-20: 3; 2014-03-21: 8
D3: | 24 | 2014-03-20: 6; 2014-03-21: 18
357 beregnet av deloppgavene…
KTN classdiagram. We were pretty unusre of the task and therfore used more time.
4.03 --> One person sick another one occupied in meetings.